## Sheet1
TEMPLATE UPLOAD MASTER SITE PROGRESS | [8 empty] | IC_000010 | TSS_000030 | IC_000030 | IC_000040 | IC_000070 | IC_000080 | IC_000090 | IC_000100 | IC_000115 | RFOA | RFOA | RFOA | Blocking Issues | Issue Owner | ACPT_000020
POIN v2 | 2016-12-01 | NOKIA | [6 empty] | Ready For Installation | Technical Site Survey - RBS | Material Delivered to Site | TI Installation Finish | G900 MHz ON AIR | 1800 MHz ON AIR | 2100 MHz ON AIR | U900 Mhz ON AIR | LTE 1800 MHz - 10 MHz - ON AIR | Full OA | Full OA | Full OA | Installation & Commissioning Issues | Issue Owner | RAN Acceptance Visit
check master site info | check master site info | check master site info | check master site info | check master site info | check master site info | check master site info | check master site info | check master site info | date | date | date | date | date | date | date | date | date | date | date | free text | free text | free text | date | free text | free text | free text | please ignore blank | please ignore blank | please ignore blank | please ignore blank
NOKIA | NOKIA | SITE_ID | SITE_NAME | PROGRAM | WBS_STATUS | REGION | PROJECT | NOKIA | IC_000010_AF | TSS_000030_AF | IC_000030_AF | IC_000040_AF | IC_000070_AF | IC_000080_AF | IC_000090_AF | IC_000100_AF | IC_000115_AF | Baseline Finish | Actual Finish | Actual Week | IC_ISSUES | IC_OWNER | ACPT_000020_AF | NOKIA | NOKIA | NOKIA | NOKIA | NOKIA | NOKIA | NOKIA
ID | BOQ No | Site ID | Site Name | SOW Category | Site Status | Region Code | Phase Name | NE Name | RFI | TSS | MOS | Installed | G900 | G1800 | U2100 | U900 | L1800 | ON AIR Baseline | ON AIR Date | ON AIR Week | IC_ISSUES | IC_OWNER | ATP Date | ATP Method | Partner NI | Indosat PIC | Update By | Update Date | Upload ID | Status
100001 | LTE15MHZ0001 | 08BKT003 | L_AUR_KUNING2 | Activation LTE 15 Mhz + Modernization RF Modul | Active | NS | LTE 15 MHz | BTS | 2017-01-18
100002 | LTE15MHZ0002 | 08PAD002 | ANDURING | upgrade TRX (EGSM) + Replace Filter | Active | NS | LTE 15 MHz | BTS | 2017-01-19
100003 | LTE15MHZ0003 | 08PAD002 | ANDURING | Retune Filter Only | Active | NS | LTE 15 MHz | BTS | 2017-01-20